CONCEPT NOTE: INCEPTION MEETING FOR THE WHO AFRO NETWORK OF PARTNER INSTITUTIONS (PILLAR 2) PROJECT

1. Title: Project Inception, Planning, and Team Coordination Meeting for the WHO AFRO Pillar 2: Enhancing Health Workforce Development for SRHR.

2. Aim: To convene the core JKUAT project team to formally launch the project, align on the technical approach, develop a detailed operational plan, and strategize for effective collaboration with WHO AFRO and other stakeholders.

3. When: Tuesday, 20th – Wednesday, 21st January 2026.

4. Venue: African Institute for Capacity Development (AICAD), Jomo Kenyatta University of Agriculture and Technology (JKUAT), Kenya.

5. Format: In-person working sessions.

Introduction

Jomo Kenyatta University of Agriculture and Technology (JKUAT), through the Department of Statistics and Actuarial Sciences (STACS), is leading a critical component under Pillar 2 (Enhancing Health Workforce Development for SRHR) of the WHO AFRO Network of Partner Institutions Initiative. This project focuses on generating evidence to address the profound challenges in the Sexual and Reproductive Health and Rights (SRHR) workforce across Africa, including shortages, inequitable distribution, and gaps in competencies.

To ensure a strong, coordinated, and impactful start, this two-day inception meeting is essential. It will bring together the multidisciplinary JKUAT team to:

- Deliberate a shared understanding of the project's objectives and deliverables.

- Review the proposed methodology and workplan.

- Plan the detailed execution of the three core phases: Evidence Synthesis, Development & Validation, and Dissemination.

- Strategize on stakeholder engagement, communication with WHO AFRO, and knowledge translation.

- Finalize preparations for the upcoming project inception meeting with WHO AFRO scheduled for 27th January 2026.

This meeting is the foundational step to transform the project proposal into actionable, timely, and high-quality outputs that will inform regional policy and investments in the SRHR workforce.

Why this Inception Meeting?

To ensure the JKUAT-led consortium is fully aligned, operationally ready, and strategically positioned to deliver on its commitments under the WHO AFRO Pillar 2 initiative with excellence and cohesion.

Specific Objectives

- To officially launch the project and align all team members on the goals, scope, and expected outcomes.

- To conduct a deep dive into the available data, literature, and tools for the Evidence Synthesis phase.

- To brainstorm and agree on the detailed "modus operandi" for each project phase, including roles, timelines, and quality assurance mechanisms.

- To plan for effective collaboration with NWU and other potential partners.

- To develop a clear agenda, presentation materials, and key messages for the upcoming WHO AFRO inception meeting.

- To produce a consolidated project roadmap and immediate action plan for the first quarter of 2026.

Structure and Agenda

DAY 1: TUESDAY, 20TH JANUARY 2026 – PROJECT LAUNCH & STRATEGIC ALIGNMENT

| Time | Activity | Lead | Purpose/Outcome |
| --- | --- | --- | --- |
| 7:45 – 8:00 | Arrival & Registration | All | Formal registration of participants. |
| 8:00 – 8:15 | Official Welcome & Introductions | Prof. Anthony Waititu | Open the meeting, set the tone, and foster team cohesion. |
| 8:15 – 9:00 | Presentation: Project Objectives & Detailed Agenda | Dr. Joseph K. Mung’atu | Ensure a common understanding of the project's aim, phases, and deliverables. |
| 9:00 – 9:45 | Presentation: Available Materials & Data Landscape | Dr. Joseph K. Mung’atu | Review existing resources, data sources, and identify immediate gaps for the Evidence Synthesis phase. |
| 9:45 – 10:00 | Address: JKUAT Grant Management Procedures | JKUATES Representative | Clarify financial, administrative, and reporting protocols for the team. |
| 10:00 – 10:20 | Tea Break | All |  |
| 10:20 – 11:30 | Brainstorming Session: Modus Operandi & Workflows | Dr. Jane A. Akinyi | Generate consensus on team coordination, communication channels, file sharing, and milestone tracking. |
| 11:30 – 12:00 | Keynote Address: The Regional HRH Context & Expectations | Dr. James Asamani (WHO AFRO) | Align team efforts with regional priorities and understand the stakeholder landscape (Virtual/Pre-recorded). |
| 12:00 – 12:15 | Partner Perspective: The Role of NWU | Prof. Christmal Christmals | Define collaboration modalities, expectations, and contribution areas from NWU (Virtual/Pre-recorded). |
| 12:15 – 13:00 | Plenary Discussion: Reactions & Implications | All, moderated by Prof. Anthony Waititu | Internalize external inputs and adjust project planning accordingly. |
| 13:00 – 14:00 | Lunch Break |  |  |
| 14:00 – 15:00 | Working Session: Formation of Thematic Sub-Groups | Dr. Charity Wamwea | Establish focused groups for the core project phases (e.g., Evidence Synthesis Group, Modeling & Analysis Group, Dissemination Group). |
| 15:00 – 16:30 | Parallel Group Work: Initial Phase Planning | Group Leads | Each group begins detailing activities, tools, and timelines for their respective phase. |
| 16:30 – 17:00 | Tea Break |  |  |
| 17:00 | Closure of Day 1 | Prof. Waititu | Summary of day’s achievements and preview of Day 2. |

DAY 2: WEDNESDAY, 21ST JANUARY 2026 – OPERATIONAL PLANNING & ROADMAPPING

| Time | Activity | Lead | Purpose/Outcome |
| --- | --- | --- | --- |
| 7:45 – 8:00 | Arrival & Registration | All |  |
| 8:00 – 8:15 | Recap of Day 1 | Dr. Winnie Chacha | Reinforce key decisions and transitions to Day 2 objectives. |
| 8:15 – 10:00 | Presentations: Group Work Outputs | Group Leads | Each sub-theme group presents their preliminary operational plan for feedback. |
| 10:00 – 10:20 | Tea Break |  |  |
| 10:20 – 13:00 | Plenary Synthesis: Integrating Plans & Resolving Issues | Mr. Henry Kissinger Ochieng | Harmonize the sub-group plans into one coherent project plan. Identify interdependencies and resource needs. |
| 13:00 – 14:00 | Lunch Break |  |  |
| 14:00 – 15:00 | Planning Session: WHO AFRO Inception Meeting (27th Jan) | Dr. Joseph Mung’atu | Develop agenda, assign presentation roles, and prepare key materials for the external stakeholder meeting. |
| 15:00 – 16:30 | Final Working Session: Project Roadmap & Way Forward | Ms. Caro W. Mugo | Consolidate all discussions into a clear, time-bound action plan and roadmap document. Define immediate next steps. |
| 16:30 – 17:00 | Tea Break |  |  |
| 17:00 | Official Closing & Departure | Prof. Anthony Waititu | Formal closure, thanks |

Participant Allocation (10 Persons)

- Prof. Anthony Waititu (Dean, SMPS)

- Dr. Charity Wamwea (Chair, STACS)

- Dr. Joseph K. Mung’atu (Principal Investigator/Technical Lead)

- Dr. Jane A. Akinyi (Co-Investigator)

- Dr. Winnie Chacha (Co-Investigator)

- Dr. Ann Omamo (Co-Investigator)

- Mr. Henry Kissinger Ochieng (Co-Investigator)

- Ms. Caro W. Mugo (Co-Investigator)

- Dr. Matabel Odin (Co-Investigator)

- One Representative from JKUATES (Grants Office)

Budget

| Item | Description | Quantity | Unit Cost (KES) | Total (KES) | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| Venue & Catering | Medium Conference Package (per person per day). Includes: Meeting room hire, morning tea, lunch, afternoon tea, and water. | 10 persons x 2 days | 2,850 | 57,000 | 439 |
| Subtotal |  |  |  | 57,000 | 439 |
| Contingency | Unforeseen expenses @ 5% |  |  | 2,850 | 22 |
| Grand Total |  |  |  | 59,850 | 461 |

Note: USD conversion using an approximate rate of KES 130 = 1 USD. The budget is based on the provided per-person rate for a medium package and covers the core meeting logistics for the 10 participants over two days.