WHO AFRO INCEPTION MEETING

Day 2: 21st January 2026

Members Present

- Joseph Mung’atu – Principal Investigator

- Matabel Odin - Member

- Charity Wamwea - Member

- Anne Omamo - Member

- Caroline Mugo - Member

- Henry Kissinger - Member

- Anthony Waititu - Member

- Jane Akinyi - Member

- Winnie Chacha - Member

- Jackson Kwanza – DVC RPE

- David	- JKUATES

Preamble

- Meeting began at 9:35am.

- Opening prayer by Dr. Ann Omamo.

- Recap of the Minutes of Day 1

- Members present missing in the minutes: Dr. Jane Akinyi and Eric-JKUATES

- Minute corrections tracked with a different color.

- Caroline Mugo has proposed. Matabel Odin has seconded.

- Track 1: Evidence Synthesis

- To be done by all

- Find out which data WHO has.

- Look for key indicators.

- Agree on what data to collect.

- Proposed Data points:

- HRH Variables

- Health Workforce Density (Stock Data)

- DALYs per capita

- GDP per capita

- Universal Health Coverage (UHC) Service Coverage Indicator (SCI) :

www.who.int/data/indicators/indicator-details/GHO/uhc-index-of-service-coverage

- Other Additional Variables

- Year (2000-2024)

- Population Size

- Sex

Agreed: Redistribute tasks to each member per country

- Budget Items

- Amount received so far is $9,375

- Amount converted at KSh. 128.3 per dollar

Acceptable Travel Related Expenses:

- Field Workers Incentives

- Per diem

- Hotel Accommodation

- Bank Charges (3%)

- Upcoming Deliverables

- Technical Report to be done by 15th February 2026

- Inception Meeting Monday 26th January 2026.

- Inception Meeting

- Date: Monday, 26th January 2026

- Time: 1pm-2pm

- Venue: COPAS Boardroom, 3rd Floor

- Expectations: Timelines, Road map with clear deliverables, Updates on Progress, Introduction, Future plans, Presentation.

- Word from Prof. Kwanza

- Congrats for winning bid by WHO.

- Working with UN requires delivery.

- Success with UN agency will open doors for other contracts.

- Ensure you work with the timelines.

- Way Forward

- Inception Meeting Presentation: Member Introduction, Partnership Mandate, and Progress Status.

- Share Day 1 and Day 2 minutes.