WHO AFRO INCEPTION MEETING AT THE AICAD

Members Present:

Joseph Mung’atu

Anthony Waititu

Henry Kissinger

Caroline Mugo

Charity Wamwea

Winnie Chacha

Matabel Odin

Ann Omamo

David

Agenda

- Deliberate a shared understanding of the project’s objectives and deliverables

- Review the proposed methodology and workplan

- Plan the detailed execution of the three phases

- Strategize on stakeholder engagement, communication with WHO AFRO and knowledge translation

- Finalize preparations for the upcoming project inception meeting with WHO AFRO

Meeting started with a word of prayer from Matabel at 8.45 am

Dr. Mung’atu took the team through the workshop program.

Official Welcome:

Prof. Waititu opened the meeting officially

He thanked the PI for the initiative and expressed that the school and University are happy about the project.

He also thanked the team members and JKUATES as well.

Members were urged to give their best output and promised full support as the dean.

Project Objectives and Detailed Agenda

Dr. Mung’atu gave an overview of the project objectives and detailed agenda.

He emphasized on the need for models that can be validated. This will be based on existing standard practices.

He took members through previous work done and project gap required to be filled.

He mentioned that funders do not have concrete evidence from the models that actually result in economic growth.

Come up with models in health workforce investment area.

Grant Management Procedures

David gave a clarification of JKUATES fund management

Imprest, re-imbursement, LOE

Any salary above 24,000 deduct a WHT of 5%

Imprest is not taxed but you need to account

He explained the whole process of requesting funds.

Accounting needs to be done within 2 weeks and any member can be given the funds.

Do not restrict the per diem to the JKUAT rates because of the low budget.

Brainstorming Session-  Jane

What is the ask/goal?

Evidence generation using scientific methods.

Linking investments in HRH to outcomes

Determine how much countries should invest in HRH

Support the generation of the HRH report

Success metrics

A model/models

Dashboards

Manuscripts and reports

Excel-based model/ R-shiny for use in countries that actualizes the model

How do we help them actualize what they want?

Have the model granulized to other cadres

Tracks- Evidence Synthesis, Modelling and analysis, Dissemination

Develop monitoring tools i.e the models, what is the progression towards the goal?

Christmals- NWU are yet to begin the project, but they have begun the systematic review as they wait for the inception meeting on the 26th.

Afternoon

Reviewed phases of project implementation

- Evidence Synthesis- Team lead-Jane

To be done by all

- Modelling and analysis- Team lead- Winnie

To be done by all

- Dissemination- team lead- Mung’atu

- Main Report

- Publications 2-3

- Policy Brief

- Fact sheets for country

4. Secretariat- Team lead-Kissinger.

How do we measure the variables coming into the model?

Teams need to familiarize themselves with the state of health workforce 2022, the health strategy, Health Charter, and Needs based assessment for the region.

Missing data

At the evidence synthesis stage, teams to collect information from the different sites.

Obtain information from MoH, MoE, Ministry of Finance and harvest the missing data.

Identify the gaps from the data and give which variables we need?

What is the modelling approach?

We need to dig into the smaller models that could inform us of what we are seeing in the bigger model.

Could we have proxies to measure the variables being used as input?

Impact- Economic Production

To be measured using GDP, GDP per capita

Outcomes

Total DALYS,

HALE

Health security

Life years saved

Job years created

Determinants of health index

Health inequalities

Service Coverage-Output

SC for communicable, infectious diseases, RMNCH

Service coverage Index for NCD, RMNCH and infectious diseases

Service Coverage should be 80%

Health workforce availability

Density for medical doctors, Density for nurses, Density for midwives, pharmaceutical staff and Dentist.

Having a model with the data (the in-service training and incentives data) getting into the model

If we have data on stock (no health workforce per population) work backwards and get the in-service training and incentives data.

Threshold is 44.5 per 10,000 is the density threshold.

Have appropriate assumptions on health workforce availability.

What is the evidence that in service training and incentives improve health workforce performance?

What proportion of investments should go into the different input aspects (in service training, incentives, education, employment and retention)?

How much investment should go into health workforce availability, health workforce performance and service coverage?

How much investment should go into health outcomes and economic production?

Another Deliverables:

Have a tool that can be used to measure the impact of the investment.

Entry point of the work

Abuja declaration- 15% of funds to go into health. This covers all national health issues

Health investments pillars, HRH should have a proportion of the 15% of e.g then go into the model so that HRH fits into the bigger health budget. Come from the total budget HRH gets a proportion then jump into it.

First line analytics

Out of the total health budget what is the efficient proportion that can be allocated to health workforce to achieve 80% of service coverage? - This is an optimization problem

2nd line analytics

Once we have proportion of budgets that go into HRH, one of the methods is to use MPT to optimize what goes into training, employment, retention to achieve a certain level of stock.

Additionally, on the same budget, what goes into in service training, incentives to achieve a certain level of service coverage. These are the proportions.

Push these proportions into a hypothetical model to determine the economic impact.

Health investments are:

HRH, Health workforce, infrastructure, health data systems, health technologies and products, leadership and governance and health service delivery.

We propose during the inception meeting we can develop a simple questionnaire based on the brainstorming that can be circulated to the countries.

Check on data on Kenya work report

Meeting closed by Prof. Waititu