TERMS OF REFERENCE

The State of Health Workforce in African Region – 2nd Edition 
To be attached to the Stellis requisition

- Background

Using a pre-COVID-19 pandemic data from a survey conducted in 2018-2019, WHO AFRO produced the first comprehensive report on the State of Health Workforce in the African Region in 2021. The evidence revealed that over the last two decades, the African region has made modest progress in health workforce development with a remarkably increase in investments in training and education infrastructure, increasing the number of health professions education institutions to about 4000 from less than 1000 in 2005. For example, more than 400 institutions are now training doctors and dentists compared with 168 institutions 20 years ago. Similarly, more than 2,200 nursing and midwifery schools are compared to less than 1,000 two decades ago. The region can now train at least 150,000 health professionals annually. The number of nurses and midwives trained annually increased from 26,000 in 2005 to at least 60,000 currently, with 65% being women. During the same period, the training of doctors also increased from roughly 6,000 to about 28,600 per year, with 28% female. As a result, between 2013 and 2020, the Region has added at least one million doctors, dentists, nurses, midwives and pharmacists (a net increase of 32%), increasing the stock from 1.8 million to 2.8 million in 2020. The African Region is also gathering momentum in investing in community health workers (CHWS), increasing its CHWs stock by 170% over the last decade from 179,968 in 2005 to 486,186 in 2018. Between 2018 and 2021, the supply of community health workers increased by 76%, from 486,186 CHWs in 2018 to almost 853,500. Over time, the profiles of CHW have steadily improved in the quality of education, selection and certification. Despite the progress, the Region continues to face a critical shortage of health workers. Projections suggest that the region could face a 5.3 million shortage of Doctors, Nurses, Midwives, Pharmacists and Dentists by 2030, which would likely constitute 52% of the anticipated global health workforce (HWF) crises by 2030. At the midpoint of the SDGs and an even greater impetus to achieve universal health coverage (UHC) and reorient health systems towards primary health care approaches, the importance of the health workforce is even more paramount, especially in the aftermath of the COVID-19 pandemic which left legacies of health worker shortages and pronounced labour market mismatches. In 2022, WHO AFRO supported Member States to update the National Health Workforce Account (NHWA) leading to 45 out of 47 countries sharing updated HWF data with WHO. Additionally, about 20 countries have conducted health labour market analysis (HLMA) since the beginning of the SDGs. With the development of the African Health Workforce Investment Charter and other continental initiatives to stimulate HWF policy and investment action, it has become necessary to undertake a comprehensive desk assessment using available evidence to update the state of health workforce in Africa. Thus, aim of the 2nd edition of the state of the Health Workforce in the African region is to provide a comprehensive picture of the health workforce dimensions including each HRH country profile of the 47 Members States in order to measure the progress toward UHC in 2030.

- Tasks & Deliverables

Tasks to be performed by the Consultant will include but not be limited to: The Consultant (s), under the guidance of WHO technical staff, will support and/or undertake the following tasks: - Conduct data triangulation and analysis (including data mining as appropriate) of all available data and evidence from NHWA, HLMA reports and published literature on the health workforce covering the following areas: - Review of a 10-year trends in the stock and density of health workers in the Region and per country (an analysis of data in NHWA v2 – data currently available with some gaps) – disaggregate by country types: HIC, LMIC, East, Southern Africa, West Africa and Central Africa; WHO SSL 2023; by cadres - Training and Education capacities in the Region (Update from the previous report – for countries, there is new data on the training capacity of 2022) - Overview of the Labour flows (inflows and out-flows), including migration – synthesis from HLMA reports – 13 countries. - Health workforce (un)employment (from 1st edition of State of HWF report and 13 HLMA reports – quantify annual employment of HWs and number of unemployed HWs by cadre) - Synthesis of projected supply, demand and need for health workers (to be integrated with other ongoing work). - Integrate analysis on health workforce spending and budget space (use paper by Pascal et al 2023 + projection from AFRO model). - State of health workforce governance and stewardship/leadership (use dataset collected in NHWA v2 AFRO + from 1st edition of State of HWF report) - Explore reasons for the observed trends and the impact of HWF on health and socio-economic indicators. - Assessment of key performance indicators compared to targets/thresholds (to be finalised after the main analysis). - Recommended actions for the next of half of the SDG era, 2025 – 2030. - From the above analysis, produce the 2nd edition of the State of Health Workforce in the African region. - Based on the Regional HRH profile, produce posters and PowerPoint summarizing the key findings of the regional HWF Deliverables will be in line with the ToR, and will include but not be limited to: At different stages of the assignment, the Consultant shall deliver the following: - Plan of analysis and structure of the report (27 January 2024) - Draft report of 2nd edition of the state of the African Health Workforce (14 February 2024) - Final report of the 2nd edition of the state of the African Health Workforce (21 February 2024) - Regional HRH profile and PowerPoint summary presentation of the regional state of HWF (28 February 2024). Documents to be provided to the consultants: - 2024 release (2023 data) of national Health Workforce Accounts (NHWA) - HLMA reports and survey datasets from 12 countries. - UHC Monitoring dataset. - Relevant publications

- Qualifications, experience, skills and languages

Desired background and experience The suitable candidate should meet the following requirements: EDUCATIONAL BACKGROUND Required: Advanced university degree (Masters or higher) in statistics, health economics, demography, public health or a quantitative field of the health sciences /social sciences. Desirable: A doctorate degree in any of the above-motioned fields. Advanced IT skills, good command of statistical applications such as STATA, SPSS, R, and Microsoft Excel. WORK EXPERIENCE Required: The candidate should have at least 7 years of experience in health workforce data analysis and/or health sector performance assessments, with experience in policy development and strategic planning. Desirable: Experience in health modelling, Health Labour Market Analysis and/or National Health Workforce Accounts. Skills and knowledge requirements: - Knowledge of tools for health workforce analysis is essential. - Quantitative data analysis using appropriate statistical software is essential. - Excellent academic writing skills as evidenced by at least 5 peer-reviewed publications in the last 2 years. - Knowledge of Human Resource Management is an added advantage. - Excellent interpersonal relationships with good negotiation skills. - Excellent facilitation and team-building skills.

- Technical Supervision

Technical supervision will be provided by Dr Adam Ahmat (Adamah@who.int) and Dr James Avoka Asamani (asamanij@who.int).

- Location: Both offsite and on-site in Brazzaville, Congo.

Please specify where the Consultant will work: Off-site: Consultants’ home country On-site for insurance purposes: WHO Regional Office, Brazzaville for 5 days. (please indicate location/address). (This is where a duty travel is planned during the course of the consultancy, but the Consultant is being hired to work from home)

- Travel - If travel is involved, full medical clearance is required – medically cleared

Please specify any expected travel(s): dates, location and purpose. Proposed travel dates: To be confirmed. A living expense is payable to on-site consultants – please refer to Information Note 08/2019 for details on eligibility.

7. Remuneration and budget (travel costs excluded)

The consultancy will be for a period of ONE Month and the consultant will be paid US$8,000 as full consideration of the work to be undertaken. Currency: USD Work schedule (if applicable) : Please refer to Information Note 09/2021 for guidance on rates for consultants.